District of Columbia Municipal Regulations


903
COMMISSIONING

Strike Chapter 9 of the International Green Construction Code in its entirety and insert new Chapter 9 in the Green Construction Code in its place to read as follows:
903.1 
General.  Where application is made for construction as described in this section, the registered design professional in responsible charge or approved agency shall perform commissioning during construction as required by Table 903.1 and by Administrative Bulletins.  The approved agency shall be qualified and shall demonstrate competence, to the satisfaction of the code official, for the commissioning of the particular type of construction or operation in accordance with the qualification requirements set forth in Administrative Bulletins.  The registered design professional in responsible charge and engineers of record involved in the design of the project are permitted to act as the approved agency provided those personnel meet the qualification requirements set forth in the Green Building Program Manual to the satisfaction of the code official. 

903.2 
Preliminary commissioning report requirement.  The approved agency shall keep records of the commissioning required by Table 903.1.  The approved agency shall furnish commissioning reports to the owner and the registered design professional in responsible charge and, upon request, to the code official.  Reports shall indicate that work was or was not completed in conformance to approved construction documents.  Discrepancies shall be brought to the immediate attention of the contractor for correction.  Where discrepancies are not corrected, they shall be brought to the attention of the owner, code official and to the registered design professional in responsible charge prior to the completion of that phase of the work.  Prior to the final inspection, a Preliminary Commissioning Report shall be provided to the owner and a copy shall be made available to the code official upon request. 

903.3 
Final commissioning report requirement.  A Final Commissioning Report shall be provided to the owner within 180 days after the date of issuance of a  the first certificate of occupancy for occupiable space in a story above grade plane, and a copy shall be made available to the code official upon request.

TABLE 903.1 

COMMISSIONING PLAN
	CONSTRUCTION OR SYSTEM REQUIRING VERIFICATION
	PREOCCUPANCY
	METHOD
	OCCURRENCE
	SECTION/
REFERENCED STANDARD

	
	
	
	Preoccupancy
	
	

	Chapter 4: Site Development and Land Use
	
	
	
	
	

	Landscape irrigation systems
	X
	Field-inspection
	Installation
	
	Section 614 of the  Plumbing Code

	Stormwater management system operation
	None
	Field-inspection
	Installation
	
	21 DCMR (Water and Sanitation), 
Chapter 5 (Water Quality and Pollution)

	Site lighting
	X
	Testing and report
	Installation
	
	409

	Chapter 6: Energy
	
	
	
	
	

	Energy consumption, monitoring, targeting and reporting
	
	
	
	
	

	a. Monitoring system
	X
	Inspection and verification
	During construction and
prior to occupancy
	
	603

	b. Calibration
	X
	Testing and review and evaluation or test reports
	During commissioning
	
	603

	Mechanical systems completion
	
	
	
	
	

	a. Air system balancing – provide the means for system balancing


	X
	Inspection and verification
	During construction and
prior to occupancy
	
	611.1.2.1 and through reference to Energy Conservation Code

	b. Hydronic system balancing – provide means for system balancing
	X
	Inspection and
verification
	During construction and
prior to occupancy
	
	611.1.2.2 and through reference to Energy Conservation Code 

	c. Mechanical system manuals – construction documents to require O&M manual
	X
	Verification of construction documents
	Plan review
	
	611.1.5.2

	Mechanical systems
	
	
	
	
	

	a. Commissioning required and noted in plans and specifications
	X
	Verification of
construction
documents
	Plan review
	
	611.1

	b. Documentation of required commissioning outcomes
	X
	Verification with the building owner
	Subsequent to completion
of all commissioning activities
	
	611.1

	c. Preparation and availability of a commissioning plan
	X
	Verification with the RDP or commissioning agent
	Between plan review and commissioning initiation
	
	611.1.1

	d. Balance HVAC systems (both air and hydronic)
	X
	HVAC system installer/contractor or commissioning agent
	After installation of HVAC systems and prior to occupancy
	
	611.1.2

	e. Functional performance testing of HVAC equipment
	X
	HVAC system installer/contractor or commissioning agent
	After installation of HVAC systems and prior to occupancy
	
	611.1.3

	f. Functional performance testing of HVAC controls and control systems
	X
	HVAC system installer/contractor or commissioning agent
	After installation of HVAC systems and prior to occupancy
	
	611.1.3.2

	g. Preparation of preliminary commissioning report
	None
	HVAC system installer/contractor or commissioning agent
	None
	
	611.1.4

	h. Acceptance of HVAC systems and equipment/system verification report
	None
	Building owner
	None
	
	611.1.4.1

	i. Preparation and distribution of final HVAC system completion. Documentation that construction documents require drawings, manuals, balancing reports and commissioning report be provided to the owner and that they have been provided
	None
	RDP, contractor or commissioning authority
	None
	
	611.1.5



	Chapter 6: Lighting
	
	
	
	
	

	Verification of lamp
	X
	Field inspection
	Final inspection
	
	611.3

	Verification of ballast
	X
	Field inspection
	Final inspection
	
	611.3

	Lighting Controls
	
	
	
	
	

	a. Installation
	X
	Field inspection
	Final inspection
	
	611.3.2

	b. Calibration
	X
	System installer/Contractor or commissioning agent
	Final inspection
	
	611.3

	Chapter 7: Water Resource Conservation, Quality and Efficiency
	
	
	
	
	

	Cooling tower performance
	—
	—
	—
	
	703.7.7

	Metering
	X
	—
	—
	
	705.1.1

	Chapter 8: Indoor Environmental Quality and Comfort
	
	
	
	
	

	Air-handling system access
	X
	Field inspection and verification
	During construction and prior to occupancy
	
	802.2

	Air-handling system filters
	X
	Field inspection and verification
	During construction and prior to occupancy
	
	802.3

	For SI: 1 square foot = 0.0929 m2.


SOURCE: Final Rulemaking published at 61 DCR 3356 (March 28, 2014 – Part 2); as corrected by Errata Notice published at 61 DCR 5246 (May 23, 2014).

The District of Columbia Green Construction Code (2013) , referred to as the “Green Construction Code,” consists of the 2012 edition of the International Green Construction Code published by the International Code Council (ICC), as amended by the District of Columbia Green Construction Code Supplement (2013)(12 DCMR K).  The International Green Construction Code is copyrighted by the International Code Council and therefore is not republished here.  However, a copy of the text may be obtained at:
http://publicecodes.cyberregs.com/icod/igcc/2012/index.htm?bu=IC-P-2012-000023&bu2=IC-P-2012-000019. 
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12-K DCMR § 903

	

	
	
	



